## Tabelle1
Week | Goal | Original estimation | Current estimation | Effort | Remain | Responsible | Status
until 05-09 | The Android App should be equipped with single text fields for the working hours in the EnterHours window. These will then make it possible in the future to have the final hours of work for each worker of a worked to the database on the next day. | 6 | 5 | 5 | 0 | Hamzic | Done
until 05-16 | The secretaries' login data will be created. With the help of this data they can log in, but they will not be forwarded to the workspace yet. | 6 | 6 | 3 | 3 | Taha, Hamzic, Djukic | Partly done
until 05-23 | The worker table, group table, group member table, and work-per-day tables will be created .With the help of these tables the workspace will be adjusted (design-technically). | 8 |  |  | 0 | Taha, Hamzic, Djukic | Not Done
until 05-30 | The group member table shows the respective foreman with the workers. With the help of a DatePicker you can select the time sheets monthly in the workspace and the work report can be displayed daily. | 6 |  |  | 0 | Taha, Hamzic, Djukic | Not Done
until 06-06 | It will be possible to create user name, password, worker name, worked hours and work report from individual windows of the app and store them in Json arrays. These arrays will be sent to the database via the rest. | 10 |  |  | 0 | Hamzic | Not Done
until 06-13 | The app successfully communicates with the database about the rest and data you write into the app will be stored in the database. The workspace successfully communicates with the database and retrieves the data stored by the app on it to output to the secretaries workspace. | 10 |  |  | 0 | Taha, Hamzic, Djukic | Not Done