## Tabelle1
Week | Goal | Original estimation | Current estimation | Effort | Remain | Responsible
until 05-09 | The Android App should be equipped with single text fields for the working hours in the EnterHours window. These will then make it possible in the future to have the final hours of work for each worker of a worked to the database on the next day. | 3 | nearly done | 2 | 1 | Hamzic
until 05-16 | Secretary accounts will be created in the database. In the workspace login, it will then be possible to log on using these to log in and then get into the actual workspace. |  | not done |  |  | Taha, Hamzic, Djukic
until 05-23 | Tables are created in the database. A group table with the individual workergroups and foremen in it. For example the workergroup Müller with the foreman Friedrich Müller. This acts as a secondary key which refers to another table. |  | not done |  |  | Taha, Hamzic, Djukic
until 05-30 | The individual foreworker groups are to be displayed in the workspace. For these, the respective work report can be selected and displayed by the date picker. By clicking on the timesheet-window the table of the respective group with the workers and working hours will be displayed. |  | not done |  |  | Taha, Hamzic, Djukic
until 06-06 | It will be possible to create user name, password, worker name, worked hours and work report from individual windows of the app and store them in Json arrays. These arrays will be sent to the database via the rest. |  | not done |  |  | Hamzic
until 06-13 | The app successfully communicates with the database about the rest and data you write into the app will be stored in the database. The workspace successfully communicates with the database and retrieves the data stored by the app on it to output to the secretaries workspace. |  | not done |  |  | Taha, Hamzic, Djukic