## Projekt 1
PM-Sheet (6)
Team: |  | Armin Hamzic, Pero Djukic and Amin Taha
Deadline: |  | 2019-06-13
Project BauX
% done | Task | Original Estimation | Current Estimation | Effort | Remain | Responsible
100% | Planung
75% | Vorbereitung
50% | Aufgabe a
25% | Aufgabe b
100% | Make the app successful communicate with the database about the rest | 5 | 5 | 5 | 0 | Hamzic
40% | Let written data in the app store in the database | 7 | 7 | 3 | 4 | Hamzic
100% | Make the workspace successful communicate with the database | 4 | 4 | 5 | 0 | Hamzic, Taha, Djukic
0%
0%